## Defect Reporting
DEFECT REPORT
DEFECT |  |  | DEFECT OVERVIEW | [5 empty] | TRACKING |  |  | FIX |  | REFERENCE ENTRY
DEFECT ID | REPORTED BY | DATE REPORTED | SUMMARY | STEPS TO REPRODUCE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | SCREENSHOT (If Any) | DEFECT PRIORITY | ASSIGNED TO | STATUS | ROOT CAUSE | COMMENTS | DEFECT PRIORITY | STATUS
PDP-001 | Sohail Abbas | 2020-05-22 | Invalid date returned if date passed in format of mm/dd/yyyy | 1. Open Url 2. Enter Data in mm/dd/yyyy format 3. Check the response 4. Expected and Actual result is different. | 28/6/2020 | Sun Jun 28 2020 00:00:00 GMT+0000 | Invalid date | Refer to test result report (TestResult_2020521174346.html) - TC #3 | Critical | Liang Zan Wong | Open |  |  | Critical | Open
PDP-002 | Sohail Abbas | 2020-05-22 | Wrong result is displayed if the date if passed in format of "Mon-YY" | 1. Open Url 2. Enter Data in "Mon-YY" format 3. Check the response. 4. Expected and Actual result is different. | June-20 | Tue Jun 30 2020 00:00:00 GMT+0000 | Wed Jun 20 2001 00:00:00 GMT+0000 | Refer to test result report (TestResult_2020521174346.html) - TC #5 & 6 | High | Liang Zan Wong | Open |  |  | High | Rejected
PDP-003 | Sohail Abbas | 2020-05-22 | Invalid Date returned if the date if passed in format of "MM-YY" or "M-YY"" | 1. Open Url 2. Enter Data in ""MM-YY" format 3. Check the response 4. Expected and Actual result is different. | 07-2020 | Wed Jul 01 2020 00:00:00 GMT+0000 | Invalid date | Refer to test result report (TestResult_2020521174346.html) - TC #7, 14 | High | Liang Zan Wong | Open |  |  | Medium | Deffered
PDP-004 | Sohail Abbas | 2020-05-22 | Wrong Year is displayed after parsing if the date is passed in "DD-Mon" or "DDMon" format | 1. Open Url 2. Enter Data in ""DD-Mon" format 3. Check the response 4. Expected and Actual Year is different. | 28-Jun | Sun Jun 28 2020 00:00:00 GMT+0000 | Thu Jun 28 2001 00:00:00 GMT+0000 | Refer to test result report (TestResult_2020521174346.html) - TC #9, 20 | Critical | Liang Zan Wong | Open |  |  | Low | Fixed
PDP-005 | Sohail Abbas | 2020-05-22 | Date is still displayed if the Invalid date is passed, which is wrong. | 1. Open Url 2. Enter Wrong Date in ""DD-MM-YYYY" format 3. Check the response 4. Wrong date is also parsed and displayed as result | 31-Jun-2020 | Invalid date | Wed Jul 01 2020 00:00:00 GMT+0000 | Refer to test result report (TestResult_2020521174346.html) - TC #18 | Critical | Liang Zan Wong | Open |  |  |  | Closed
PDP-006 | Sohail Abbas | 2020-05-22 | Date of 2001 is displayed if we pass incomplete date which is wrong. | 1. Open Url 2. Enter incomplete date (0,1,2) 3. Check the response 4. Date of 2001 is displayed, which is wrong | 0 | Invalid date | Sat Jan 01 2000 00:00:00 GMT+0000 | Refer to test result report (TestResult_2020521174346.html) - TC #21,22,23 | High | Liang Zan Wong | Open
PDP-007 | Sohail Abbas | 2020-05-22 | Date is still displayed if we pass 4 digit random number, which is wrong. | 1. Open Url 2. Enter random year (1234) 3. Check the response 4. Date is displayed, which is wrong | 1234 | Invalid date | Sun Jan 01 1234 00:00:00 GMT+0000 | Refer to test result report (TestResult_2020521174346.html) - TC #25 | Low | Liang Zan Wong | Open